## PROD
STAGE 1 | [7 empty] | Status:
ENV. | SEV. | Action | Scope | Status | Assigned to | Approved by | Comments | Planned
PROD | HIGH | Blocked accounts with read and write permissions on Azure resources should be removed | svc_dbaasmiguat@db.com | Unassigned | Alexadru | Manprit | Terraform module, | In progress
|  |  | svc_dbaasmigprd@db.com | Unassigned |  |  | Access review for automation | Resolved
|  |  | vinodh_raj.kumararajan@db.com | Unassigned |  |  | Manprit for approval, Alexandru for implement | Resolved via 3rd party
PROD | HIGH | Add co-owner to the subscription | O365 Azure KV PROD 1 Subscription | Unassigned | Alexandru | Manprit |  | Resolved with mitigation
|  |  | PROD AAD/O365 Monitoring | Unassigned |  |  |  | Risk accepted
|  |  | O365 Azure KV PROD 2 Subscription | Unassigned
|  |  | PRD - AZCP Infrastructure | Unassigned
PROD | HIGH | Reduce list of subscription owners to maximum of 3 | Prod - CSO Monitoring | Unassigned | Alexandru | Manprit | CyberArk PAM in progress
|  |  | EUC Microsoft Azure Enterprise | Unassigned
|  |  | GNS TEST | Unassigned
|  |  | Prod AAD\O365 | Unassigned
|  |  | Tier Zero Subscription | Unassigned
|  |  | DBaaS-APP-UAT-01 | Unassigned |  |  | Approval for AMA should go through DB processes. It should de identified with Alistair's help. Testing of AMA is in process already by Alexandru in DEV.
|  |  | ACP_APPPRD_152799-2_MicrosoftIntune | Unassigned |  |  | AMA Policy in DEV is alread enabled for security events in VMs - WI and Linux
PROD | HIGH | Install Log Analytics agent on virtual machines | 17 VMs (look at "VMs to log") | Unassigned | Alexandru |  | Approval for AMA should go through DB processes. It should de identified with Alistair's help. Testing of AMA is in process already by Alexandru in DEV. AMA Policy intiative in DEV is already enabled for security events in VMs both Win and Linux
PROD | HIGH | Machines should be configured to periodically check for missing system updates | jenkins-tf-lab/GNS TEST | In progress | Alexandru |  | VM should be removed
PROD | HIGH | VM should encrypt disks and data flows between Compute and Storage resources | jenkins-tf-lab/GNS TEST | In progress | Alexandru |  | VM should be removed
PROD | HIGH | Linux VMs should enable Azure Disk Encryption or EncryptionAtHost | 37 VMs (look at "VMs to Encrypt") | In progress | Alexandru
PROD | HIGH | Secure transfer for storage accounts should be enabled | lbtestbootdiagnstics | In progress | Ivan Bylina |  | Enforced by Azure Policy with Modify effect
|  |  | gnsimages | In progress | Ivan Bylina
|  |  | gbaz01wer0001rgdiag | In progress | Ivan Bylina
|  |  | gbaz02wer0001rgdiag | In progress | Ivan Bylina
|  |  | dbaasfaeuwp000a | In progress | Ivan Bylina
|  |  | dbaasfaeuwu000a |  | Ivan Bylina |  | This storage account is in UAT
PROD | HIGH | FTPS should be required in function apps | func-db-spo-site-enforcer-api-prod | In progress | Alexandru | Manprit | Planned to be impleneted by Azure Policy and Terraform. Approved already by Manprit
|  |  | func-db-spo-site-enforcer-prod | In progress | Alexandru
PROD | HIGH | Automation account variables should be encrypted | 55 Automation accounts | In progress | Alexandru
STAGE 2
PROD | HIGH | Enable Microsoft Defender for Key Vault |  | Resolved
PROD | HIGH | Key vault keys should have an expiration date | dbWORM_100101-1 | Unassigned
PROD | HIGH | Enable Microsoft Defender for DNS |  | Unassigned
PROD | HIGH | Enable Microsoft Defender for App Service |  | Resolved
PROD | HIGH | Microsoft Defender for API should be enabled | EUC Microsoft Azure Enterprise | Unassigned
PROD | HIGH | Microsoft Defender for Storage should be enabled | Prod - CSO Monitoring | Unassigned
PROD | HIGH | Microsoft Defender for Resource Manager should be enabled | ACP_APPPRD_152799-2_MicrosoftIntune | Unassigned
|  |  | EUC Microsoft Azure Enterprise | Unassigned
PROD | HIGH | Microsoft Defender for Azure SQL DB servers should be enabled | DBaaS-APP-UAT-01 | Unassigned
PROD | HIGH | SQL managed instances should have vulnerability assessment configured | dbdbsmigbsu0z15/DBaaS-APP-UAT-01 | Unassigned
|  |  | dbdbsmigbsup0rie/DBaaS-APP-PRD-01 | Unassigned
Note on A3: Artem Sinitsyn: 16 High, 12 Med, 21 Low with 51 unassigned
Note on A6: Artem Sinitsyn: 16 High, 12 Med, 21 Low with 51 unassigned
Note on C6: Artem Sinitsyn: across 15 subs No modify perms for EPAM!
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No modify perms for EPAM!

## UAT
Env. | Severity | Action | Scope | Status | Assigned to
UAT | HIGH | Add co-owner to the subscription | O365 Azure KV UAT 1 Subscription | Unassigned
|  |  | O365 Azure KV UAT 2 Subscription | Unassigned
|  |  | UAT_127875-1_db-chatbot-platform | Unassigned
UAT | HIGH | Reduce list of subscription owners to maximum of 3 | AZCP Infrastructure | Unassigned
|  |  | UAT AAD\O365 | Unassigned
|  |  | UAT - CSO Monitoring, | Unassigned
|  |  | dbWORM_100101-1_UAT | Unassigned
UAT | HIGH | Enable Azure Disk Encryption\Encryption at Host and install Defender for Cloud | db-runner-win-uat-01 | Unassigned
UAT | HIGH | Enable Azure AD authentication for | sql-server-enforcer-test | Unassigned
UAT | HIGH | Disable Blob public access in Storage Account settings |  | Unassigned
UAT | HIGH | Secure transfer to storage accounts should be enabled | dbaasfaeuwu000a | Unassigned
|  |  | storageaccountdbaasad82 | Unassigned
|  |  | storageaccountdbaasbff4 | Unassigned
|  |  | cs210033fff9cff3dd4 | Unassigned

## VMs to log
resourceGroup | resourceName | resourceType
rg-eas-pr-01 | hkazu01cmp0001n | Virtual machines
rg-eas-dn-01 | hkazu01edh0002n | Virtual machines
rg-sea-pr-01 | sgazu01cmp0001n | Virtual machines
rg-sea-dn-01 | sgazu01edh0002n | Virtual machines
rg-gno-dn-01 | skagn002 | Virtual machines
rg-gwc-dn-01 | skazf002 | Virtual machines
rg-gno-pr-01 | swazb001 | Virtual machines
rg-gwc-pr-01 | swazf001 | Virtual machines
rg-ukw-pr-01 | ukazu01cmp0002n | Virtual machines
rg-uks-dn-01 | ukazu01edh0001n | Virtual machines
rg-uks-pr-01 | ukazu01wbp0001n | Virtual machines
rg-uks-dn-01 | ukazu01edh0003n | Virtual machines
rg-ukw-dn-01 | ukazu01edh0004n | Virtual machines
rg-cus-pr-01 | ukazu01cmp0001n | Virtual machines
rg-eus-pr-01 | ukazu01cmp0002n | Virtual machines
rg-eus-dn-01 | ukazu01edh0003n | Virtual machines
rg-cus-dn-01 | ukazu01edh0004n | Virtual machines

## Exceptions
To address - You recognize that the improvement action is necessary and plan to address it at some point in the future. This state also applies to actions that are detected as partially, but not fully completed.
Planned - There are concrete plans in place to complete the improvement action.
Risk accepted - Security should always be balanced with usability, and not every recommendation will work for your environment. When that is the case, you can choose to accept the risk, or the remaining risk, and not enact the improvement action. You won't be given any points, but the action will no longer be visible in the list of improvement actions. You can view this action in history or undo it at any time.
Resolved through third party and Resolved through alternate mitigation - The improvement action has already been addressed by a third-party application or software, or an internal tool. You'll gain the points that the action is worth, so your score better reflects your overall security posture. If a third party or internal tool no longer covers the control, you can choose another status. Keep in mind, Microsoft will have no visibility into the completeness of implementation if the improvement action is marked as either of these statuses.